## Sheet1
| Action Plans | Responsible Parties | Original Timeframe | Comments
GOAL 1 ¦ IMPLEMENT UPTON CENTER REVITALIZATION
1.1 | Use a business and residents needs survey to help develop plans for the second phase of Upton Center Revitalization Project. | EDC Town Planner | 2021 | Completed, although the RFC had no responses.
1.2 | Use the survey data to create a new Request for Proposals (RFP) for Upton Center Revitalization. Post a revised RFP to the Central Register. | EDC Town Planner | 2021 | Completed, although the RFC had no responses.
1.3 | Support development of the Community Center at May Town Meeting. | EDC and CCBC | Completed | Completed.
1.4 | Coordinate with MA DOT District 3 on Rte. 140 TIP Project to minimize impact with potential Community Center and Upton Center development projects. | EDC, DPW, Town Planner | 2022-23 | The TIP becomes a factor in the downtown revitalization goals.
1.5 | Work with DPW on the Complete Streets Prioritization Plan for Upton Center | EDC and DPW | 2021 | No EDC activity. DPW owns Complete Streets, but maybe EDC could still assist within the context of overall vision.
GOAL 2 ¦ IDENTIFY POTENTIAL IMPROVEMENTS FOR WEST UPTON CENTER
2.1 | Review current zoning by-laws in West Upton Center. Determine if there are any by-laws that should be updated. | EDC, Planning Board, Town Planner | 2021 | A continuing process, driven by other activities such as Affordable Housing and the MBTA program.
2.2 | Create design guidelines for West Upton Center similar to those created for Upton Center | EDC, Planning Board, Town Planner | 2022 | Planned under earmark funding.
2.3 | Coordinate with MassDOT District 3 on Hartford Ave/High Street TIP Project and keep residents informed of project impact. | EDC, DPW, Town Planner | 2021-21 [sic] | TIP project is done. EDC had limited input.
2.4 | Review Complete Streets Prioritization Plan in West Upton Center. | EDC, DPW, Town Planner | 2022 | See 1.5.
2.5 | Coordinate with MassDOT District 3 on the Rte 140 TIP project to assess impact to West Upton Center and Upton Center. | EDC, DPW, Town Planner | 2022-23 | Still a potential.
GOAL 3 ¦ STREAMLINE MUNICIPAL PROCEDURES
3.1 | Add an Economic Development page to the Town Website. | EDC and Tech Committee | 2021 | Done, and directly linked from the home page under "Doing Business".
3.2 | Create an Upton Small Business resource guide to help small businesses that want to locate in Upton. | EDC and Town Planner | 2021-23 | Steve Rakitin started this. We need to determine status.
3.3 | Enhance online permitting software currently being used by the Town of Upton. | EDC and various departments | 2022 | New software is implemented. Michael and Amy are working through issues.
3.4 | Create a new business intake process to help new businesses by providing assistance navigating town bylaws and zoning regulations. | EDC and Town Planner | 2022 | Michael taking lead role. He can meet with businesses and offer services, including a Welcome to Town. Need to have a plan for higher visibility.
GOAL 4 ¦ FOSTER BUSINESS GROWTH
4.1 | Inventory existing businesses and vacancies in commercial and industrial zones to determine mix, needs, and opportunities. | EDC and local realtors | 2023 | A possible partnership with Placer.AI coule help with the "needs and opportunities" determination.
4.2 | Conduct a study of infrastructure needs throughout Upton. | EDC and town departments | 2023 | Planned under earmark funding.
4.3 | Promote the use of vacant buildings as business incubators. | EDC and local realtors | 2022
4.4 | Update list of small business and home business listings and post/maintain listing on town website. | EDC | 2022 | Created in 2021 and listed on the home page. Updating is an issue; Michael will work with town licensing processes.
4.5 | Promote creation of a small business association and encourage business owners to participate. | EDC and local business leaders | 2023 | Business networks already exist and there would be little return on adding another. We could host a meeting to enable businesses to share town-specific concerns.
4.6 | Consider CMRPC Brownfields Program for any necessary remediation of commercial/ industrial property. | EDC and Town Planner | 2023
4.7 | Work with Blackstone Valley Chamber of Commerce to host a local Upton Business Roundtable. | EDC and Town Planner | 2022
4.8 | Work with local businesses on hosting regular events such as Farmer’s Market/Artisan Fairs. | EDC and local businesses | 2021 | Some effort is being put into this.
GOAL 5 ¦ LEVERAGE EXISTING CULTURAL RESOURCES AND PUBLIC UTILITIES
5.1 | Leverage existing State Forest Land and town conservation land to help transform Upton into an ecotourism destination. | EDC, Open Space and Land Steward Committees | 3-5 years | We should post information on existing walks for example via Facebook groups or the Historical Society.
5.2 | Explore expanding existing Walking Tour of Upton to include Milhaus, Town Hall, Bradish House and other historical sites with the goal to expand cultural tourism. | EDC, Historical Commission, Historical Society | 3-5 years
5.3 | Develop a commuter survey for Upton residents to determine commuting patterns and plan accordingly. | EDC and CMRPC | 2022 | For these goals, we could again use Pacer.ai tools to assess our needs and opportunities. For example, the twon could use data to ask WRTA or MBTA to provide services using land (for example on Westboro Road). CMRPC's transit group may be able to provide guidance.
5.4 | Determine if and how a local Regional Transit Authority service could benefit Upton residents. | EDC and Town Planner | 3+ years
5.5 | Assess feasibility of creating a transit hub. Identify potential State resources that could help. | EDC and State | 5+ years
5.6 | Promote potential sites suitable for large-scale solar energy battery storage or similar projects. Ensure adequate utility infrastructure is included in plans. | EDC and State | 3-5 years